# Cyclistic bike share Data Analysis

## Data Analyst: Luigi Tallarico

## Client/Sponsor:

Chief Marketing Director Lily Moreno
Cyclistic Executive Team.

## Purpose:

The primary business objective is converting casual riders into annual members in order to maximize financial income, since annual members are much more profitable than casual ones.

The specific data analysis task hereby outlined to support this objective is to analyze historical bike trip data to identify trends of how annual members and casual riders differ.

The results will be shared with the executive team to be considered and either approved or rejected.

## Scope / Major Project Activities:

| Activity | Description |
| --- | --- |
| Data Collection | Collect data about casual and member riders bike usage. |
| Process and Analyze Data | Analyze behavioural patterns in the last year by week and season. Compare results between the two groups. |
| Identify possible marketing solutions. | Suggest applicable marketing strategies to improve the conversion rate of casual riders into members. |
| Deliver Final Report | Share results and insights with the Marketing Director and the Executive Team. |

## This project does not include:

- This project doesn’t consider data outside the period ranging from 2025-05 to 2026-04

- This project analyzes only time patterns, not including geographical data.

- This project analyzes historical data and does not predict future data.

## Deliverables:

| Deliverable | Description/ Details |
| --- | --- |
| Dashboard | An interactive data visualization dashboard. |
| Recommendations | A list of data-driven recommendations. |
| Final Report | A final report detailing the analysis results and possible marketing solutions. |

## Schedule Overview / Major Milestones:

| Milestone | Expected Completion Date | Description/Details |
| --- | --- | --- |
| Data Review and Preparation | 08/06/2026 | Review of all data sources and identify its flaws. |
| Data analysis | 09/06/2026 | Data analysis completed in SQL |
| Dashboard creation | 09//06/2026 | Dashboard visualization created |
| Recommendations list | 09/06/2026 | List of recommendations for marketing |
| Final report | 10/06/2026 | Final report detailing all work, analysis, methodologies, and findings. |

## *Estimated date for completion:

June 10 2026